## Sheet1
Related User Story | Task Description |  | Initial Estimate | Amount Remaining After…
Team Member
|  |  |  | Week 1 | Week 2 | Week 3 | Week 4
Data Storage | Create Server | Team
Data Storage | Develop server data storage functionality | Team
Manage Employee Requests | Create employee requests UI | Destiny | 2
Manage Employee Requests | Develop employee requests functionality | Destiny | 20
Manage Employee Requests | Create Employee requests feature wireframe and documentation | Destiny | 5
Edit Employee Profile | Develop Editing functionality for employee profile | Brianna | 7
See Employee Work Schedule | Create work schedule UI | Brianna | 3
Edit Employee Profile | Develop Editing functionality for employee hours | Brianna | 7
View Hours | Add hours worked to landing page UI | Brianna | 2
Hr wants to see employees schedule and hrs worked | Display the schedule and hrs worked of the selected employee | Miguel | 5
Hr wants to edit employees schedule and payment | Develop editing functionality for the schedule and payment of the selected employee | Miguel | 5
Hr wants to interact with the employees requests | Create employees request list UI | Miguel | 3
Hr wants to interact with the employees requests | Develop editing/respond functionality | Miguel | 8
Schedule meetings with HR | Develop UI for employee meeting schedule | Fernando | 2
Calculate Weekly Pay | Develop functionality to calculate pay | Fernando | 2
Schedule meetings with HR | Develop functionality to schedule meeting | Fernando | 4
| Estimate Totals |  | 75 | 0 | 0 | 0 | 0