## Sheet1
Related User Story | Task Description | Team Member | Initial Estimate | Amount Remaining After…
|  |  |  | Week 1 | Week 2 | Week 3
Code Structure | Login Page MVVM Refactor | Brianna | 4 | 0 | 0 | 0
Code Structure | Landing Page MVVM Refactor | Brianna | 6 | 0 | 0 | 0
Employee Profile | Functionality for Editing Own Profile | Brianna | 3 | 2 | 0 | 0
Data Storage | Server Employee Profile Storage | Brianna | 5 | 4 | 3 | 0
Employe Profile | Profile Management for Server | Brianna | 2 | 2 | 2 | 0
Testing | Add test cases for Employee Time | Brianna | 1 | 0 | 0 | 0
Testing | Add test cases for Server | Brianna | 2 | 2 | 0 | 0
Manage Employee Requests | Split HR Requests View into Pending and Completed Listviews | Destiny | 1 | 0 | 0 | 0
Manage Employee Requests | Split Employee Requests View into Pending and Completed Listviews | Destiny | 1 | 0 | 0 | 0
Manage Employee Requests | Modify functionality to support split list views on Employee side | Destiny | 3 | 0 | 0 | 0
Manage Employee Requests | Modify functionality to support split list views on HR side | Destiny | 3 | 1 | 0 | 0
Data Storage | Server Employee Request Storage | Destiny | 4 | 4 | 1 | 0
Data Storage | Server Functionality for Managing Employee Request | Destiny | 6 | 6 | 3 | 0
Testing | Add test cases for Employee Request Manager | Destiny | 1 | 1 | 0 | 0
Testing | Add test cases for the Employee Manager | MIguel | 5 | 2 | 0 | 0
Documentation | Add jacoco to the pom file | MIguel | 1 | 1 | 1 | 0
Refactoring | Refactor HR Page | MIguel | 2 | 2 | 2 | 0
Documentation | Update class diagram | Fernando | 4 | 3 | 2 | 0
Documentation | Update wireframes | Fernando | 1 | 1 | 1 | 0
Documentation | Update use case scenarios | Fernando | 2 | 2 | 1 | 0
Testing | Add test cases for JSON methods | Fernando | 2 | 2 | 2 | 0
Testing | Update Employee Profile test cases | Fernando | 1 | 1 | 1 | 0
| Estimate Totals |  | 60 | 36 | 19 | 0