## Sheet1
Related User Story | Task Description |  | Initial Estimate | Amount Remaining After…
Team Member
|  |  |  | Week 1 | Week 2 | Week 3 | Week 4
Data Storage | Develop server | Team | 5 | 2 | 0 | 0 | 0
Data Storage | Develop client | Team | 6 | 0 | 0 | 0 | 0
Data Storage | Develop functionality to store employee credentials on server | Brianna | 10 | 4 | 2 | 1 | 0
Manage Employee Requests | Create UI for viewing current requests for employee | Destiny | 2 | 0 | 0 | 0 | 0
Manage Employee Requests | Create UI for adding a new work request | Destiny | 2 | 2 | 0 | 0 | 0
Manage Employee Requests | Develop functionality for adding a new work request | Destiny | 5 | 5 | 2 | 1 | 0
Manage Employee Requests | Create Employee requests feature wireframe and documentation | Destiny | 3 | 2 | 1 | 0 | 0
Employee Clockin | Create UI for viewing multiple clockins a day | Brianna | 2 | 2 | 2 | 0 | 0
Employee Clockin | Refactor Clockin feature to support muliple clockins | Brianna | 5 | 3 | 3 | 0 | 0
View Hours | Add hours worked to landing page UI | Brianna | 1 | 1 | 1 | 0 | 0
Hr landing page refactoring | Refactor the distribution of the button in the page, textfields, etc | Miguel | 1 | 0 | 0 | 0 | 0
Hr landing page refactoring | Create a UI for the add employee page functionality | Miguel | 2 | 0 | 0 | 0 | 0
Hr landing page refactoring | Develop functionality for adding a new employee profile | Miguel | 5 | 4 | 1 | 1 | 0
Hr wants to interact with the employees requests | Create employees request list UI | Miguel | 1 | 1 | 1 | 0.3 | 0.3
Hr wants to interact with the employees requests | Develop editing/respond functionality | Miguel | 4 | 4 | 4 | 2 | 0
Log Out | Add Log Out Functionality | Fernando | 2 | 0 | 0 | 0 | 0
Documentation | Update Class Diagram to include new functionality | Fernando | 3 | 3 | 1 | 0 | 0
Documentation | Update Use Case Diagram to include new functionality | Fernando | 1 | 1 | 1 | 1 | 0
Documentation | Add Use Cases for New Functionality | Fernando | 5 | 5 | 3 | 0 | 0
Documentation | Update system wireframe to include new functionality UI | Fernando | 3 | 3 | 0 | 0 | 0
| Estimate Totals |  | 68 | 42 | 22 | 6.3 | 0.3