## Sheet1
Related User Story | Task Description |  | Initial Estimate | Amount Remaining After…
Team Member
|  |  |  | Week 1 | Week 2 | Week 3 | Week 4
User wants to login | Create login page UI | Destiny | 1 | 1 | 0 | 0 | 0
User wants to login | Complete validation functionality for login credentials | Destiny | 10 | 10 | 4 | 0 | 0
Employee wants to clock in/out for work | Develop clocking in and out feature for employee | Brianna | 7 | 7 | 3 | 3 | 1
HR wants to create an employee profile | Create employee profile page UI | Fernando | 2 | 2 | 1 | 1 | 1
HR wants to create an employee profile | Develop employee profile creation functionality | Fernando | 5 | 5 | 2 | 1 | 0
HR wants to create schedules & HR wants to calculate pay | Create employee summary page UI for HR | Miguel | 4 | 4 | 4 | 2 | 0
HR wants to view all employees at company | Develop functionality that allows HR to view a master list of all employees | Miguel | 8 | 7 | 6 | 4 | 0
User wants to view landing page | Create UI for landing page | Brianna | 3 | 3 | 3 | 0 | 0
| Estimate Totals |  | 40 | 39 | 23 | 11 | 2